## Team
Members
Initials | First | Last | Email | GitHub Username
JN | Jessica | Noel | jnoel@stevens.edu | jnoel01
BP | Brendan | Probst | bprobst@stevens.edu | brendanprobst
JS | John | Schneiderhan | jschnei4@stevens.edu | jshneiderhan15
GitHub Repo: https://github.com/jnoel01/WeBeAgile

## Backlog
Backlog
Sprint | Story Id | Story Name | Owner | Status
1 | US01 | Reformatting Original Script | JN | Done
1 | US02 | Storing ID-Age | BP | Done
1 | US03 | Storing Gender-Death Date | JS | Done
1 | US04 | Storing Child-Husband | JN | Done
1 | US05 | Storing Spouse-Divorce | BP | Done
1 | US06 | Determine Marriage Date before Death | JS | Done
2 | US07 | Fewer than 5 children per family | BP | Done
2 | US08 | Child born at least 9 months after parents marriage | JS | Done
2 | US09 | Child born before mother's death | BP | Done
2 | US10 | Death should be less than 150 years after birth | JN | Done
2 | US11 | Marriage should be more than 18 years after birth of either spouse | JS | Done
2 | US12 | Father's death must be more than 9 months before child's birth | JN | Done
3 | US13 | No more than five siblings born at the same time | JN | Coding
3 | US14 | No more than 15 siblings in the whole family | JN | Coding
3 | US15 | Parents can not marry descendants | BP | Coding
3 | US16 | Siblings can not marry | BP | Coding
3 | US17 | First cousins can not marry | JS | Done
3 | US18 | Correct gender for role | JS | Done
4 | US19 | All individuals IDs should be unique | JN | Planning
4 | US20 | No more than one individuals with the same name and birthdate | JN | Planning
4 | US21 | No more than one child with the same first name | BP | Planning
4 | US22 | List all deceased individuals in a GEDCOM file | BP | Planning
4 | US23 | List all living married people in a GEDCOM file | JS | Planning
4 | US24 | List all livigng people over 30 who have never marrtied | JS | Planning

## Burndown
Burndown
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2022-09-23 | 24 | - | - | - | -
Sprint 1 | 2022-10-03 | 18 | 6 | 93 | 64 | 87.1875
Sprint 2 | 2022-10-17 | 12 | 6 | 39 | 42 | 55.7143
Sprint 3 | 2022-10-28 | 6 | 6 | 98 | 160 | 36.75
Sprint 4 | 2022-11-07 | 0 | 6

## Sprint 1
Sprint 1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates After Current Date | JS | Done | 23 | 15 | 12 | 10 | TRUE
US02 | Birth Before Marriage | JN | Done | 20 | 20 | 11 | 5 | TRUE
US03 | Birth Before Death | JN | Done | 18 | 25 | 11 | 10 | TRUE
US04 | Marriage Before Divorce | JS | Done | 7 | 20 | 11 | 10 | TRUE
US05 | Marriage after Death | BP | Done | 11 | 25 | 11 | 4 | TRUE
US06 | Divorce before Death | BP | Done | 14 | 10 | 37 | 25 | TRUE
|  |  |  | Estimated LOC | Estimated Time | LOC | Time
REVIEW RESULTS |  |  |  | 93 | 115 | 93 | 64
Keep Doing: -Making flexible functions -Communicating on good meeting times -Communicate while coding through messaging
Avoid: -GitHub conflicts - Rewriting already written code - Writing functions that do more than 1 thing

## Sprint 2
Sprint 2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US07 | Fewer than 5 children | BP | Done | 6 | 10 | 6 | 3 | TRUE
US08 | Child born at least 9 months after parents marriage | JS | Done | 20 | 15 | 13 | 9 | TRUE
US09 | Child born before mother's death | BP | Done | 15 | 10 | 8 | 12 | TRUE
US10 | Death should be less than 150 years after birth | JN | Done | 7 | 10 | 4 | 5 | TRUE
US11 | Marriage should be more than 18 years after birth of either spouse | JS | Done | 25 | 15 | 14 | 15 | TRUE
US12 | Father's death must be less than 9 months before child's birth | JN | Done | 12 | 18 |  |  | TRUE
|  |  |  | Estimated LOC | Estimated Time | LOC | Time
|  |  |  | 85 | 78 | 39 | 41
REVIEW RESULTS
Keep Doing: - Communicating on what needs to be done - following code conventions - thinking about how your code affects other developers
Avoid: - saving things for the last minute - using ambiguous language when discussing tasks that need to be done

## Sprint 3
Sprint 3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US13 | No more than five siblings born at the same time | JN | Done | 12 | 10 | 10 | 20 | TRUE
US14 | No more than 15 siblings in the whole family | JN | Done | 12 | 10 | 10 | 20 | TRUE
US15 | Parents can not marry descendants | BP | Done | 15 | 15 | 15 | 30 | TRUE
US16 | Siblings can not marry | BP | Done | 9 | 8 | 17 | 30 | TRUE
US17 | First cousins can not marry | JS | Done | 17 | 8 | 26 | 40 | TRUE
US18 | Correct gender for role | JS | Done | 17 | 12 | 20 | 20 | TRUE
|  |  |  | Estimated LOC | Estimated Time | LOC | Time
|  |  |  | 82 | 63 | 98 | 160
REVIEW RESULTS
Keep Doing: - Supporting each other when help is needed on our own tasks - Understanding the functions will be hard and prepare selves for that - Being productive during meetings
Avoid: - Missing meetings with the team - Talking over each other during meetings

## Sprint 4
Sprint 4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US19 | Unique Id's | JN | Planning | 6 | 10 |  |  | FALSE
US20 | Unique name and birthdate | JN | Planning | 10 | 15 |  |  | FALSE
US21 | Unique first name | BP | Planning | 5 | 10 |  |  | FALSE
US22 | List deceased | BP | Planning | 15 | 10 |  |  | FALSE
US23 | List living married | JS | Planning | 15 | 10 |  |  | FALSE
US24 | List living single | JS | Planning | 13 | 10 |  |  | FALSE
|  |  |  | Estimated LOC | Estimated Time | LOC | Time
|  |  |  | 64 | 65 | 0 | 0
REVIEW RESULTS
Keep Doing: -
Avoid: -

## Stories
Stories
Story ID | Story Name | Story Description
US01 | Reformatting Original Script | Alter the code and get rid of parts that are not needed from Project 2
US02 | Storing ID-Age | Store the values of the string/data from the individual "line" column "ID through Age"
US03 | Storing Gender-Death Date | Store the values of the string/data from the individual "line" column "Gender through Death"
US04 | Storing Child-Husband | Store the values of the string/data from the individual "line" column "Child through Husband"
US05 | Storing Spouse-Divorce | Store the values of the string/data from the individual "line" column "Spouse through Divorce"
US06 | Determine Marriage Date before Death | Determining that the marriage date happens before death: error checking
US07 | No more than 5 kids | Fewer than 5 children per family
US08 | Valid birth after marriage | Child born at least 9 months after parents marriage
US09 | Mother alive for child birth | Child born before mother's death
US10 | Max Age 150 | Death should be less than 150 years after birth
US11 | Can only marry at 18+ | Marriage should be more than 18 years after birth of either spouse
US12 | Father must be alive for conception | Father's death must be more than 9 months before child's birth
US13 | No more than 5 kids at the same time | No more than five siblings born at the same time
US14 | No more than 15 siblinsg total | No more than 15 siblings in the whole family
US15 | Can not marry descendants | Parents can not marry descendants
US16 | Can not marry siblings | Siblings can not marry
US17 | can not marry first cousins | First cousins can not marry
US18 | Correct gender for role | Aunts and Uncles can not marry their neices or nephews
US19 | Unique Id's | Husband in family should be male and wife in family should be female
US20 | Unique name and birthdate | No more than one individuals with the same name and birthdate
US21 | Unique first name | No more than one child with the same first name
US22 | List deceased | List all deceased individuals in a GEDCOM file
US23 | List living married | List all living married people in a GEDCOM file
US24 | List living single | List all livigng people over 30 who have never marrtied