## Team
Members
Initials | First | Last | Email | GitHub Username
JN | Jessica | Noel | jnoel@stevens.edu | jnoel01
BP | Brendan | Probst | bprobst@stevens.edu | brendanprobst
JS | John | Schneiderhan | jschnei4@stevens.edu | jshneiderhan15
GitHub Repo: https://github.com/jnoel01/WeBeAgile

## Backlog
Backlog
Sprint | Story Id | Story Name | Owner | Status
1 | US01 | Reformatting Original Script | JN | Done
1 | US02 | Storing ID-Age | BP | Done
1 | US03 | Storing Gender-Death Date | JS | Done
1 | US04 | Storing Child-Husband | JN | Done
1 | US05 | Storing Spouse-Divorce | BP | Done
1 | US06 | Determine Marriage Date before Death | JS | Done
2 | US07 | Fewer than 5 children per family | BP | Done
2 | US08 | Child born at least 9 months after parents marriage | JS | Done
2 | US09 | Child born before mother's death | BP | Done
2 | US10 | Death should be less than 150 years after birth | JN | Done
2 | US11 | Marriage should be more than 18 years after birth of either spouse | JS | Done
2 | US12 | Father's death must be more than 9 months before child's birth | JN | Done
2 | US 13 | No more than five siblings born at the same time | JN | Planning
1 | US14 | No more than 15 siblings in the whole family | JN | Planning
2 | US15 | Parents can not marry descendants | BP | Planning
1 | US16 | Siblings can not marry | BP | Planning
2 | US17 | First cousins can not marry | JS | Planning
2 | US18 | Aunts and Uncles can not marry their neices or nephews | JS | Planning

## Burndown
Burndown
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2022-09-23 | 24 | - | - | - | -
Sprint 1 | 2022-10-03 | 18 | 6 | 93 | 64 | 87.1875
Sprint 2 | 2022-10-17 | 12 | 6 | 497 | 42 | 710
Sprint 3
Sprint 4

## Sprint 1
Sprint 1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates After Current Date | JS | Done | 23 | 15 | 12 | 10 | TRUE
US02 | Birth Before Marriage | JN | Done | 20 | 20 | 11 | 5 | TRUE
US03 | Birth Before Death | JN | Done | 18 | 25 | 11 | 10 | TRUE
US04 | Marriage Before Divorce | JS | Done | 7 | 20 | 11 | 10 | TRUE
US05 | Marriage after Death | BP | Done | 11 | 25 | 11 | 4 | TRUE
US06 | Divorce before Death | BP | Done | 14 | 10 | 37 | 25 | TRUE
|  |  |  | Estimated LOC | Estimated Time | LOC | Time
REVIEW RESULTS |  |  |  | 93 | 115 | 93 | 64
Keep Doing: -Making flexible functions -Communicating on good meeting times -Communicate while coding through messaging
Avoid: -GitHub conflicts - Rewriting already written code - Writing functions that do more than 1 thing

## Sprint 2
Sprint 2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US07 | Fewer than 5 children | BP | Done | 6 | 10 | 6 | 3 | TRUE
US08 | Child born at least 9 months after parents marriage | JS | Done | 20 | 15 | 13 | 9 | TRUE
US09 | Child born before mother's death | BP | Done | 15 | 10 | 8 | 12 | TRUE
US10 | Death should be less than 150 years after birth | JN | Done | 7 | 10 | 4 | 5 | TRUE
US11 | Marriage should be more than 18 years after birth of either spouse | JS | Done | 25 | 15 | 14 | 15 | TRUE
US12 | Father's death must be less than 9 months before child's birth | JN | Done | 12 | 18 |  |  | TRUE
|  |  |  | Estimated LOC | Estimated Time | LOC | Time
|  |  |  | 85 | 78 | 39 | 41
REVIEW RESULTS
Keep Doing: - Communicating on what needs to be done - following code conventions - thinking about how your code affects other developers
Avoid: - saving things for the last minute - using ambiguous language when discussing tasks that need to be done

## Sprint 3
Sprint 3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US13 | No more than five siblings born at the same time | JN | Planning | 12 | 10 |  |  | FALSE
US14 | No more than 15 siblings in the whole family | JN | Planning | 12 | 10 |  |  | FALSE
US15 | Parents can not marry descendants | BP | Planning | 15 | 15 |  |  | FALSE
US16 | Siblings can not marry | BP | Planning | 9 | 8 |  |  | FALSE
US17 | First cousins can not marry | JS | Planning | 17 | 8 |  |  | FALSE
US18 | Aunts and Uncles can not marry their neices or nephews | JS | Planning | 17 | 12 |  |  | FALSE
|  |  |  | Estimated LOC | Estimated Time | LOC | Time
|  |  |  | 82 | 63 | 0 | 0

## Sprint 4
Sprint 4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US19 |  | JN | [5 empty] | FALSE
US20 |  | JS | [5 empty] | FALSE
US21 |  | BP | [5 empty] | FALSE
US22 |  | JN | [5 empty] | FALSE
US23 |  | JS | [5 empty] | FALSE
US24 |  | BP | [5 empty] | FALSE
|  |  |  | Estimated LOC | Estimated Time | LOC | Time
|  |  |  | 0 | 0 | 0 | 0

## Stories
Stories
Story ID | Story Name | Story Description
US01 | Reformatting Original Script | Alter the code and get rid of parts that are not needed from Project 2
US02 | Storing ID-Age | Store the values of the string/data from the individual "line" column "ID through Age"
US03 | Storing Gender-Death Date | Store the values of the string/data from the individual "line" column "Gender through Death"
US04 | Storing Child-Husband | Store the values of the string/data from the individual "line" column "Child through Husband"
US05 | Storing Spouse-Divorce | Store the values of the string/data from the individual "line" column "Spouse through Divorce"
US06 | Determine Marriage Date before Death | Determining that the marriage date happens before death: error checking
US07 | No more than 5 kids | Fewer than 5 children per family
US08 | Valid birth after marriage | Child born at least 9 months after parents marriage
US09 | Mother alive for child birth | Child born before mother's death
US10 | Max Age 150 | Death should be less than 150 years after birth
US11 | Can only marry at 18+ | Marriage should be more than 18 years after birth of either spouse
US12 | Father must be alive for conception | Father's death must be more than 9 months before child's birth
US 13 | No more than 5 kids at the same time | No more than five siblings born at the same time
US14 | No more than 15 siblinsg total | No more than 15 siblings in the whole family
US15 | Can not marry descendants | Parents can not marry descendants
US16 | Can not marry siblings | Siblings can not marry
US17 | can not marry first cousins | First cousins can not marry
US18 | Can not marry neices or nephews | Aunts and Uncles can not marry their neices or nephews