## Team
Members
Initials | First | Last | Email | GitHub Username
JN | Jessica | Noel | jnoel@stevens.edu | jnoel01
BP | Brendan | Probst | bprobst@stevens.edu | brendanprobst
JS | John | Schneiderhan | jschnei4@stevens.edu | jshneiderhan15
GitHub Repo: https://github.com/jnoel01/WeBeAgile

## Backlog
Backlog
Sprint | Story Id | Story Name | Owner | Status
1 | US01 | Reformatting Original Script | JN | TRUE
1 | US02 | Storing ID-Age | BP | TRUE
1 | US03 | Storing Gender-Death Date | JS | TRUE
1 | US04 | Strogin Child-Husband | JN | TRUE
1 | US05 | Storing Spouse-Divorce | BP | TRUE
1 | US06 | Creating Pretty Table | JS | TRUE

## Burndown
Burndown
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2022-09-14 | 32 | - | - | - | -
Sprint 1 | 2022-09-23 | 24 | 6 | 93 | 109 | 51.1927
Sprint 2
Sprint 3
Sprint 4

## Sprint 1
Sprint 1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Reformatting Original Script | JN | DONE | 6 | 15 | 23 | 25 | TRUE
US02 | Storing ID-Age | JS | DONE | 8 | 20 | 20 | 15 | TRUE
US03 | Storing Gender-Death Date | BP | DONE | 10 | 25 | 18 | 12 | TRUE
US04 | Strogin Child-Husband | JN | DONE | 8 | 20 | 7 | 10 | TRUE
US05 | Storing Spouse-Divorce | BP | DONE | 9 | 25 | 11 | 5 | TRUE
US06 | Creating Pretty Table | JS | DONE | 6 | 10 | 14 | 42 | TRUE
REVIEW RESULTS
Keep Doing: -Writing Pseudo Code -Communicating Meeting Time -Helping each other when there is a blocker
Avoid: -Writing over each others code -Giving variables complicated names -Showing up Hungry -Stale pretzels when hungry

## Sprint 2
Sprint 2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US07 |  | JN | [5 empty] | FALSE
US08 |  | JS | [5 empty] | FALSE
US09 |  | BP | [5 empty] | FALSE
US10 |  | JN | [5 empty] | FALSE
US11 |  | JS | [5 empty] | FALSE
US12 |  | BP | [5 empty] | FALSE

## Sprint 3
Sprint 3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US13 |  | JN | [5 empty] | FALSE
US14 |  | JS | [5 empty] | FALSE
US15 |  | BP | [5 empty] | FALSE
US16 |  | JN | [5 empty] | FALSE
US17 |  | JS | [5 empty] | FALSE
US18 |  | BP | [5 empty] | FALSE

## Sprint 4
Sprint 4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US19 |  | JN | [5 empty] | FALSE
US20 |  | JS | [5 empty] | FALSE
US21 |  | BP | [5 empty] | FALSE
US22 |  | JN | [5 empty] | FALSE
US23 |  | JS | [5 empty] | FALSE
US24 |  | BP | [5 empty] | FALSE

## Stories
Stories
Story ID | Story Name | Story Description
US01 | Reformatting Original Script | Alter the code and get rid of parts that are not needed from Project 2
US02 | Storing ID-Age | Store the values of the string/data from the individual "line" column "ID through Age"
US03 | Storing Gender-Death Date | Store the values of the string/data from the individual "line" column "Gender through Death"
US04 | Strogin Child-Husband | Store the values of the string/data from the individual "line" column "Child through Husband"
US05 | Storing Spouse-Divorce | Store the values of the string/data from the individual "line" column "Spouse through Divorce"
US06 | Creating Pretty Table | Install & import PrettyTable for Python, then implement it to format the data columns in two piles: invidiuals and families